## Approval Tracker
Magic Scarf — Client Approval Tracker
One row per page × component. Customer signs each off via column status. Owner column tracks who is responsible. Use comments column for change requests.
Color key: Green = approved · Yellow = customer reviewing · Red = blocked / change requested · Blue = WizCommerce internal
Total rows | 85
Approved | 0
In review | 85
Blocked | 0
Approval % | 0%
# | Page / View | Component / Section | Owner (WizComm) | Owner (Magic Scarf) | Status | Sign-off date | Customer comments | Resolved by
1 | Global | Logo + wordmark fallback | Design + Eng | — | In review
2 | Global | Brand color (Magic Burgundy #8B2942) | Design + Eng | — | In review
3 | Global | Type pairing (Cormorant + Inter) | Design + Eng | — | In review
4 | Global | Announcement bar copy + perks | Design + Eng | — | In review
5 | Global | Sticky header layout | Design + Eng | — | In review
6 | Global | Search pill UX | Design + Eng | — | In review
7 | Global | Mobile drawer nav | Design + Eng | — | In review
8 | Global | Footer 5-column layout + brand block | Design + Eng | — | In review
9 | Global | Toll-free phone in footer + announce + contact | Design + Eng | — | In review
10 | Global | Social links (Facebook + YouTube only) | Design + Eng | — | In review
11 | Home | Hero copy + dual CTAs | Design + Eng | — | In review
12 | Home | Hero figure (rotator image selection) | Design + Eng | — | In review
13 | Home | Hero thumb strip (manual carousel) | Design + Eng | — | In review
14 | Home | Trust line under hero CTAs | Design + Eng | — | In review
15 | Home | Seasonal Categories rail (6 tiles) | Design + Eng | — | In review
16 | Home | Magic Scarf Catalog grid (17 tiles) | Design + Eng | — | In review
17 | Home | Brand Story band copy | Design + Eng | — | In review
18 | Home | Story stats (20+ years / 12k retailers / 900+ SKUs) | Design + Eng | — | In review
19 | Home | Trade-show schedule preview (4 cards) | Design + Eng | — | In review
20 | Home | Faire band copy + CTA | Design + Eng | — | In review
21 | Home | Wholesale signup band | Design + Eng | — | In review
22 | Catalog | Catalog grid (17 categories) | Design + Eng | — | In review
23 | Catalog | Category descriptions | Design + Eng | — | In review
24 | PLP — Ponchos | Subcategory pill bar | Design + Eng | — | In review
25 | PLP — Ponchos | Filter sidebar (Subcat / Color / Material / Pattern / Stock) | Design + Eng | — | In review
26 | PLP — Ponchos | Sort dropdown options | Design + Eng | — | In review
27 | PLP — Ponchos | Product card layout (SKU + chips + price-locked) | Design + Eng | — | In review
28 | PLP — Ponchos | Pagination | Design + Eng | — | In review
29 | PLP — Scarves & Shawls | Audited description copy | Design + Eng | — | In review
30 | PLP — Scarves & Shawls | 7 audited subcategory pills | Design + Eng | — | In review
31 | PLP — Best Picks | Layout + 16-card grid | Design + Eng | — | In review
32 | PLP — Sale | Discount badge styling | Design + Eng | — | In review
33 | PDP — 8672 Cashmere Poncho | Gallery (sticky main + 4 thumbs) | Design + Eng | — | In review
34 | PDP — 8672 Cashmere Poncho | Audited description verbatim | Design + Eng | — | In review
35 | PDP — 8672 Cashmere Poncho | 47-color variant grid + named labels | Design + Eng | — | In review
36 | PDP — 8672 Cashmere Poncho | Sourcing strip (case-pack / MOQ / 24h) | Design + Eng | — | In review
37 | PDP — 8672 Cashmere Poncho | Login-gated price box | Design + Eng | — | In review
38 | PDP — 8672 Cashmere Poncho | Trust strip (4 icons) | Design + Eng | — | In review
39 | PDP — 8672 Cashmere Poncho | 4 accordions (Details / Specs / Shipping / Care) | Design + Eng | — | In review
40 | PDP — 8672 Cashmere Poncho | Related Products always-fills-to-4 | Design + Eng | — | In review
41 | PDP — 7777 Victorian Lace | Heritage badge + description | Design + Eng | — | In review
42 | PDP — 2997 Magnetic Brooch | Accessory PDP layout (different sourcing) | Design + Eng | — | In review
43 | Cart | Empty state | Design + Eng | — | In review
44 | Cart | Cart row layout (image + meta + qty stepper + remove) | Design + Eng | — | In review
45 | Cart | Sticky summary sidebar (login-gated subtotal) | Design + Eng | — | In review
46 | Account | Sidebar with avatar + tier pill | Design + Eng | — | In review
47 | Account | KPI tiles (open orders / cart / Net-30) | Design + Eng | — | In review
48 | Account | Recent orders table | Design + Eng | — | In review
49 | Show Schedule | 8-card full grid | Design + Eng | — | In review
50 | Show Schedule | Real 2026–2027 calendar (CUSTOMER TO SUPPLY) | Design + Eng | — | In review
51 | Contact | Contact form (7 fields + topic select) | Design + Eng | — | In review
52 | Contact | Reach card (phone / email / hours / showroom) | Design + Eng | — | In review
53 | Login modal | Split panel layout | Design + Eng | — | In review
54 | Login modal | Promo panel copy | Design + Eng | — | In review
55 | Register modal | 11 audited fields + tier dropdowns | Design + Eng | — | In review
56 | Register modal | Apply for Wholesale promo | Design + Eng | — | In review
57 | Search modal | Placeholder (real search wired post-launch) | Design + Eng | — | In review
58 | Mobile (375) | Card grid 2-up | Design + Eng | — | In review
59 | Mobile (375) | Hamburger drawer all 9 items | Design + Eng | — | In review
60 | Mobile (375) | PDP variant grid scrollability | Design + Eng | — | In review
61 | Mobile (375) | Sticky header height (64px) | Design + Eng | — | In review
62 | Tablet (900) | Card grid 3-up | Design + Eng | — | In review
63 | Tablet (900) | PLP body 1-col below 1100 | Design + Eng | — | In review
64 | Accessibility | Body type ≥17px (older-B2B) | Design + Eng | — | In review
65 | Accessibility | Buttons ≥52px primary | Design + Eng | — | In review
66 | Accessibility | No autoplay carousels | Design + Eng | — | In review
67 | Accessibility | Focus rings visible | Design + Eng | — | In review
68 | Accessibility | Alt text on every image | Design + Eng | — | In review
69 | Accessibility | WCAG AA contrast on body | Design + Eng | — | In review
70 | Performance | No console errors | Design + Eng | — | In review
71 | Performance | Lazy-loaded images | Design + Eng | — | In review
72 | Brand assumption | Magic Burgundy #8B2942 confirmed by customer | Design + Eng | — | In review
73 | Brand assumption | 47-color hex chips QA'd against fabric | Design + Eng | — | In review
74 | Brand assumption | Founder photo supplied | Design + Eng | — | In review
75 | Brand assumption | Showroom address confirmed | Design + Eng | — | In review
76 | Brand assumption | Founding year 2003 confirmed | Design + Eng | — | In review
77 | Backend | Real authentication wired | Design + Eng | — | In review
78 | Backend | Real cart persistence | Design + Eng | — | In review
79 | Backend | Real search | Design + Eng | — | In review
80 | Backend | Sort + filter API live | Design + Eng | — | In review
81 | Backend | Tier-pricing API | Design + Eng | — | In review
82 | Migration | SKU master CSV uploaded | Design + Eng | — | In review
83 | Migration | Variant CSV uploaded | Design + Eng | — | In review
84 | Migration | Image CDN configured | Design + Eng | — | In review
85 | Migration | 301 redirects from /stores/eol/ paths | Design + Eng | — | In review

## Sign-off
Magic Scarf — Final Sign-off
Reviewer | Role | Decision | Date | Signature
Engineering (WizCommerce)
Product (WizCommerce)
CSM (WizCommerce)
Brand owner (Magic Scarf)
Operations / Wholesale (Magic Scarf)
Approving stakeholder (Magic Scarf)